## How to use
BEST Platform — Open Questions
Purpose | Work through these with the BEST team, record their answers, then share the file back with the Chief PM to turn answers into logged decisions.
Baseline | BEST PRD – Final Rollout (unrevised as of 8 Oct 2026). Generated 9 Oct 2026 from open-questions.md in BEST-X-TBR.
Questions tab | One row per question. Read 'Ask BEST' aloud; 'Options' lists the choices. Full trade-offs are on the Options tab.
Cells to fill in | Pale yellow columns only: Chosen option, BEST's answer / notes, Answered by, Date, Follow-up needed, Status.
Internal column | Grey column 'TBR recommendation (internal)' is our view. Use the [–] button above it to collapse it before sharing your screen with BEST.
Status values | Open · Answered · Needs follow-up · Parked
⚑ | Blocks PRD sign-off. Close these first, starting with Q-01, Q-02, Q-03 and Q-07.
Example of a filled row | Q-13 → Chosen option: C · Answer: "Scheduling team uses a shared calendar; no API. Manual entry is fine for pilot." · Answered by: [name], BEST Ops · Date: 15-Oct-2026 · Follow-up: No · Status: Answered
Legend
Fill in
Internal (TBR only)

## Questions
ID | ⚑ | Question | Why it matters | PRD refs | Owner | Depends on | Ask BEST | Options | TBR recommendation (internal) | Chosen option | BEST's answer / notes | Answered by | Date | Follow-up needed | Status
Q-01 | ⚑ | In-session experience: live indicators and alerts | The single biggest driver of scope, regulatory risk, device choice and timeline. The PRD contradicts itself. | §3, §8.5, §8.6, §11 (soft alerts in MVP) vs §19.5 (never trigger alerts or prompts during live sessions) | BEST + TBR | Q-02, Q-03 | During a session, what must the therapist see: live indicators, soft alerts, or is a post-session summary enough? Is live awareness the core reason for this product? | A. Post-session only B. Live indicators, no alerts C. Indicators + soft alerts (PRD as written) | A for MVP; B and C gated on counsel's opinion (Q-02). If BEST says live awareness is the reason they're buying, B with counsel fast-tracked in parallel. | [5 empty] | Open
Q-02 | ⚑ | Regulatory pathway and FDA classification | FDA's January 2026 CDS guidance keeps software that analyses signals or patterns from continuous measurements, or makes time-sensitive outputs, under oversight. Wellness positioning requires no disease or clinical-management claims — hard for a clinical tool used in autism therapy. | §5, §14, §19 (all written to stay non-diagnostic) | BEST | — | Has BEST engaged FDA regulatory counsel? Can we get a written opinion on live alerts and trend indicators before we build them? | A. Written opinion from FDA regulatory counsel before building in-session features B. FDA Pre-Submission (Q-Sub) meeting C. Proceed on internal interpretation | A now; B only if counsel flags a grey zone. Build Option A of Q-01 while waiting. *Not legal advice — this is the product call pending counsel.* | [5 empty] | Open
Q-03 | ⚑ | Wearable selection and validation | Sensory-sensitive children may refuse to wear devices. Consumer readings in children can be unreliable. Vendor must sign a BAA (§15.1). Sync interval determines whether "live" is possible. | §8.4 (vendor-agnostic, read-only, consent-based, periodic sync), §17.2 (over-reliance on wearables) | BEST + TBR | Q-01 | Which wearable does BEST have in mind? Can we run a short comfort and data-quality test with a few children at a BEST clinic? | A. Pick one vendor now B. Vendor-agnostic layer + tolerance test of 2 shortlisted devices C. Defer devices — manual-only MVP | B. If Q-01 lands on A, sync interval stops being a hard criterion. | [5 empty] | Open
Q-04 | ⚑ | North Star Metric | No target means no way to judge the pilot. §10 lists metrics without baselines or targets. | §10 (metrics listed, no targets or baselines) | BEST + TBR | Q-01 | What single result would tell BEST this product is working? | A. Weekly active therapists B. % of sessions with a therapist-reviewed summary C. Documentation time saved per session D. % of sessions reviewed by a supervisor | B as North Star, C as guard metric. Measure the documentation-time baseline before the pilot. Revisit if Q-01 goes to C (then alert relevance matters). | [5 empty] | Open
Q-05 |  | Delivery timeline structure | Timeline depends on scope (Q-01, Q-07) and regulatory answers (Q-02). | A draft M1–M7 Gantt was produced on 2026-10-05. Treat it as draft until Q-01 and Q-07 close. | TBR | Q-01, Q-07 | Are there fixed dates BEST must hit, or can we plan around go/no-go gates? | A. Fixed date, flexible scope B. Fixed scope, flexible date C. Gate-based milestones with target windows | C — gates at counsel opinion, device test, pilot exit. | [5 empty] | Open
Q-06 | ⚑ | Stakeholders and decision rights | Decisions stall without a named owner and clinical lead. | — | BEST + TBR | — | Who is the accountable product owner at BEST, who is the clinical lead, and who signs off the PRD and final acceptance? | A. One accountable product owner at BEST, with a named clinical advisor B. Steering committee | A, plus a named clinical lead (BCBA) for Q-11 and Q-17 sign-offs. | [5 empty] | Open
Q-07 | ⚑ | Pilot customer and commercial scope | Admin, billing and back-office requirements outweigh the clinical core. Building all of it before proving therapist value delays learning. | §3, §8.9, §8.10, §11 (full licensing, billing, finance console and expense controls in MVP) | BEST | — | Who is the pilot customer (BEST's own clinics or a paying external organisation), and what result decides go/no-go? Are billing and payments needed for the pilot? | A. Full SaaS shell in MVP (PRD as written) B. Pilot in BEST's own clinics; minimal org admin; defer billing, payments, finance console, expense controls C. Multi-tenant + org admin + licensing; defer billing and payments | B if the pilot is BEST's own clinics; C if it's a paying external organisation. | [5 empty] | Open
Q-08 | ⚑ | "Clinical decision making (basic)" | Contradicts the PRD's own rule of no clinical recommendations, and is a regulatory red flag. | §3 and §11 (in MVP) vs §5.1 (no clinical recommendations), §13.2 (no automated decision making) | BEST | Q-02 | What did BEST intend by "clinical decision making (basic)" in the MVP scope? | A. Remove the phrase B. Redefine as "structured observation and documentation support" C. Keep as written | A or B. Ask BEST what they intended. | [5 empty] | Open
Q-09 | ⚑ | AI scope in the MVP | PRD sections disagree on which AI features are MVP. | §14.2 (MVP: trend highlighting, cross-session comparison, adaptive alert tuning) vs §11 (pattern detection is Phase 2) vs §19 (unphased) | BEST + TBR | Q-02 | For the MVP, is AI-drafted session summaries enough, or are pattern prompts and alert tuning expected from day one? | A. Summary drafting only B. A + post-session pattern prompts (§19) C. Full §14.2 including adaptive alert tuning | A for MVP; B in Phase 2 once enough sessions exist, matching §11. | [5 empty] | Open
Q-10 | ⚑ | Consent for the child's data and AI training | Parents are non-users yet must consent for the child. The PRD defines no consent store. | §8.4 (consent-based), §14.4 (BEST historical data may train AI), §20.6 (telehealth consent). Parents are listed as non-users (§4). No consent store is specified. | BEST | — | Who gives consent for the child's data today, how is it recorded, and does it cover using data for AI training? | A. Consent captured outside the app; admin attests in-app B. Digital consent captured at client onboarding by Org Admin, stored in an in-app consent store C. Per-session consent by therapist | B, with separate opt-ins for AI training and telehealth. Needs BEST's legal review. | [5 empty] | Open
Q-11 |  | SpO₂ and "stress" language | SpO₂ is collected but never displayed. "Stress" reads as a clinical claim. | §8.4 (collects SpO₂), §8.5 (never displays it), §8.8 ("stress trends" in summary) | BEST + TBR | Q-02 | Is SpO₂ needed in the MVP? Can "stress trends" be renamed "heart rate trends"? | A. Drop SpO₂ from MVP; rename "stress trends" → "heart rate trends" B. Collect SpO₂ but don't display; keep "stress" | A. Clinical lead to confirm wording. | [5 empty] | Open
Q-12 | ⚑ | Telehealth in the MVP | Big scope add (video vendor, consent, home device handling) and missing from §11 phasing. | §20.3 (in MVP) vs §11 (not in phasing). At home, someone must put the wearable on the child — but parents are non-users. | BEST | Q-03, Q-10 | Does BEST run remote sessions today, and at what volume? Who would put the wearable on the child at home? | A. Full telehealth in MVP B. Telehealth MVP without wearables (manual notes and markers only) C. Phase 2 | C, or B if BEST already runs remote sessions at volume. | [5 empty] | Open
Q-13 |  | Session scheduling source | Sessions can't start without schedules; the source system is undefined. | §8.2 ("Session scheduling (scheduling Dept)") — no integration defined | BEST | — | What system does the scheduling department use today, and does it have an API? | A. Integrate with BEST's existing scheduling system B. CSV import C. Manual entry in-app | C or B for pilot, A later. | [5 empty] | Open
Q-14 |  | Organization Admin access to clinical data | Least-privilege access to PHI; the PRD is silent on admin clinical access. | §15.3, §18.2 (scope is "own organization" — clinical data not addressed) | BEST | — | Should Organization Admins see any clinical session data, or only users, clients and settings? | A. No clinical access by default B. Read-only summaries C. Full access | A — clinical access only if the person also holds a clinical role. | [5 empty] | Open
Q-15 |  | Break-glass access to PHI | HIPAA governance for emergency PHI access; approver and limits not named. | §8.10, §15.3, §18.3 (reason, approval, scope, expiry, audit — but no approver or limits named) | BEST + TBR | — | Who should approve emergency access to patient data, for how long, and must the customer be notified? | A. BEST security lead approves B. Customer Org Admin approves C. Dual approval; customer notified; short time-box | C, subject to what customer BAAs allow. | [5 empty] | Open
Q-16 |  | Ownership of plans and entitlements | Two PRD sections assign plan ownership differently. | §8.10 (Platform Admin manages plans) vs §18.2 (Finance manages plans; Platform Admin manages entitlements) | BEST | — | Who owns plans and pricing (Finance) versus entitlements and configuration (Platform Admin)? | A. Split as §18.2: Finance owns plans and pricing, Platform Admin owns entitlements and config B. Single owner | A, with each side approving the other's changes that affect them. | [5 empty] | Open
Q-17 | ⚑ | Placeholder thresholds | A vendor can't build or test against words. | "sustained trends" (§8.6), "≥ N sessions" (§19.8), "minimum session count" (§19.7), "acceptable latency" (§9) | BEST | Q-01 | Who at BEST will sign off default values for "sustained trend", minimum session count and acceptable delay? | A. Fix values in the PRD now B. Configurable parameters with defaults signed off by BEST's clinical lead, tuned in pilot C. Leave to the developers | B. | [5 empty] | Open
Q-18 |  | Platform Admin vs SRE | Combined role gives broad standing access; PRD sections disagree. | §8.10 (separate permission profiles) vs §18.2 (one combined role) | TBR | — | Is it acceptable to split Platform Admin and SRE into separate roles? | A. Separate roles B. Combined (as §18.2) | A. | [5 empty] | Open

## Options
ID | Option | Name | What it means | Gains | Costs | TBR pick
Q-01 | A | Post-session only | In session: notes, markers, device status. All wearable data shown afterwards on a timeline aligned to markers. | Lowest regulatory exposure. Periodic sync (§8.4) is enough, so wider vendor choice. Simplest build, no alert tuning. Cleanly tests whether therapists value the data at all. | Drops the §2 promise of "awareness during sessions". Value arrives only after the session. BEST may see it as diluted. Least differentiated. | ✓
Q-01 | B | Live indicators, no alerts | §8.5 rising / stable / settling indicators. No push alerts. | Keeps live awareness, therapist stays in control. | Still real-time interpretation of continuous signals — in the FDA's watch zone. Needs a latency target and fast-syncing vendor; a stale "stable" is a trust problem. Real-time age-aware baselines (§5.2) are real engineering. Therapist attention is on the child, not the screen.
Q-01 | C | Indicators + soft alerts (PRD as written) | §8.5 + §8.6 in full. | The full vision. Strongest differentiation. | Highest regulatory risk — pushing an alert about a child to a clinician is the clearest step toward device classification. Liability for false or missed alerts. Tightest latency. Needs validated wearables. §19.5 contradiction must be resolved.
Q-02 | A | Written opinion from FDA regulatory counsel before building in-session features |  | Authoritative answer. Protects BEST and TBR. Cheap relative to rework. | Takes weeks. Counsel cost (budget is confidential — Sujit to confirm). | ✓
Q-02 | B | FDA Pre-Submission (Q-Sub) meeting |  | Answer from FDA itself. | Months, not weeks. Only worth it if counsel says it's a grey zone.
Q-02 | C | Proceed on internal interpretation |  | No delay. | Full regulatory risk sits with BEST, and with TBR's delivery. Not defensible if challenged.
Q-03 | A | Pick one vendor now |  | Fastest to integrate. | Single point of failure. May not suit every child.
Q-03 | B | Vendor-agnostic layer + tolerance test of 2 shortlisted devices |  | Matches §8.4. Real evidence from children before commitment. | A few weeks of testing at a BEST clinic. Needs consent for the test. | ✓
Q-03 | C | Defer devices — manual-only MVP |  | No device risk at all. | Removes the core differentiator. Barely a product.
Q-04 | A | Weekly active therapists |  | Easy to measure. | Measures logins, not value.
Q-04 | B | % of sessions with a therapist-reviewed summary |  | Tied to the documentation value. Works under any Q-01 option. | Can be rubber-stamped — needs a guard metric. | ✓
Q-04 | C | Documentation time saved per session |  | Closest to real value. | Needs a baseline measured before the pilot starts.
Q-04 | D | % of sessions reviewed by a supervisor |  | Captures supervisor value. | Secondary — depends on therapists first.
Q-05 | A | Fixed date, flexible scope |  | Predictable for BEST. | Constant scope negotiation.
Q-05 | B | Fixed scope, flexible date |  | Complete product. | Unpredictable — risky with regulatory unknowns.
Q-05 | C | Gate-based milestones with target windows |  | Honest about unknowns (counsel, device test, pilot results). Clear go/no-go points. | BEST may want hard dates. | ✓
Q-06 | A | One accountable product owner at BEST, with a named clinical advisor |  | Fast decisions. Clear accountability. | Load on one person. | ✓
Q-06 | B | Steering committee |  | Broad buy-in. | Slow. Decisions get diluted.
Q-07 | A | Full SaaS shell in MVP (PRD as written) |  | Sellable from day one. | Heaviest build. Clinical validation comes last.
Q-07 | B | Pilot in BEST's own clinics; minimal org admin; defer billing, payments, finance console, expense controls |  | Fastest to clinical value. | Commercial launch later. Architecture must still be multi-tenant from day one. | ✓
Q-07 | C | Multi-tenant + org admin + licensing; defer billing and payments |  | Ready for a first external customer without the finance stack. | Middle on both. | ✓
Q-08 | A | Remove the phrase |  | Removes the contradiction and a regulatory red flag. | None, if it never meant anything specific. | ✓
Q-08 | B | Redefine as "structured observation and documentation support" |  | Keeps intent in safe language. | Needs BEST to confirm that's what they meant. | ✓
Q-08 | C | Keep as written |  | — | Undefined, contradictory, and a gift to a regulator.
Q-09 | A | Summary drafting only |  | Lowest risk. Directly cuts documentation effort. | Less "AI" to show. | ✓
Q-09 | B | A + post-session pattern prompts (§19) |  | Distinctive insight. | Patterns need ≥ N completed sessions per child — little to show early in a pilot anyway.
Q-09 | C | Full §14.2 including adaptive alert tuning |  | Full vision. | Only meaningful if Q-01 = C. Highest risk.
Q-10 | A | Consent captured outside the app; admin attests in-app |  | Uses BEST's existing intake process. | Weak audit trail.
Q-10 | B | Digital consent captured at client onboarding by Org Admin, stored in an in-app consent store |  | Auditable, timestamped, role-linked (as §20.6 requires). | Needs a consent-store feature the PRD doesn't define. | ✓
Q-10 | C | Per-session consent by therapist |  | Very granular. | Heavy friction every session.
Q-11 | A | Drop SpO₂ from MVP; rename "stress trends" → "heart rate trends" |  | Data minimisation. Removes a clinical-sounding claim. | Loses a signal BEST may want later. | ✓
Q-11 | B | Collect SpO₂ but don't display; keep "stress" |  | Keeps data for later. | Collecting PHI with no use. "Stress" reads as interpretation.
Q-12 | A | Full telehealth in MVP |  | Matches §20. | Video vendor with BAA, consent flow, home device handling. Big scope add.
Q-12 | B | Telehealth MVP without wearables (manual notes and markers only) |  | Simple. §20.5 already makes signal overlays optional. | Less data in remote sessions.
Q-12 | C | Phase 2 |  | Keeps the MVP focused. | Delays a modality BEST may need. | ✓
Q-13 | A | Integrate with BEST's existing scheduling system |  | No double entry. | Depends on that system having an API.
Q-13 | B | CSV import |  | Cheap. | Manual and error-prone. | ✓
Q-13 | C | Manual entry in-app |  | Simplest. | Duplicate work for the scheduling team. | ✓
Q-14 | A | No clinical access by default |  | Least privilege. | Admin can't help with clinical queries. | ✓
Q-14 | B | Read-only summaries |  | Some oversight. | More PHI exposure.
Q-14 | C | Full access |  | Simple. | Violates least privilege.
Q-15 | A | BEST security lead approves |  | Fast. | Customer has no say.
Q-15 | B | Customer Org Admin approves |  | Customer control. | Slow in an incident.
Q-15 | C | Dual approval; customer notified; short time-box |  | Strongest governance. | Slightly slower. | ✓
Q-16 | A | Split as §18.2: Finance owns plans and pricing, Platform Admin owns entitlements and config |  | Separation of duties. | Needs a hand-off between teams. | ✓
Q-16 | B | Single owner |  | Simple. | Weaker controls.
Q-17 | A | Fix values in the PRD now |  | Testable. | Hard to get right before real data.
Q-17 | B | Configurable parameters with defaults signed off by BEST's clinical lead, tuned in pilot |  | Testable and adjustable. | Needs a governance step for changes. | ✓
Q-17 | C | Leave to the developers |  | — | Clinical decisions made by engineers.
Q-18 | A | Separate roles |  | Least privilege; matches §8.10. | One more role to manage. | ✓
Q-18 | B | Combined (as §18.2) |  | Simpler for a small team. | Broad standing access.

## Summary
Progress
Measure | All | ⚑ Blocks PRD
Total questions | 18 | 11
Open | 18 | 11
Answered | 0 | 0
Needs follow-up | 0 | 0
Parked | 0 | 0
% answered | 0% | 0%
By owner
Owner | Total | Still open
BEST | 9 | 9
BEST + TBR | 7 | 7
TBR | 2 | 2