## Documents
BEST · Document register
28 October 2026 · Status: Agreed = signed off internally · Draft — with client = sent for client review · Draft — internal = not yet shared · Out of date = needs refresh
Document | Format | Last updated | Status | Holds | Gap | Next action
PRD v3.1 | Word | 28 Oct 2026 | Draft — internal | Overall requirements, brought in line with all decisions to 28 Oct; Appendix A lists changes and pending items | None known. Items awaiting the client are tagged PENDING CLIENT CONFIRMATION | Share with BEST to confirm the pending items
PRD v3.1 diagrams PDF (11 figures) | PDF | 28 Oct 2026 | Draft — internal | Flow figures used in PRD v3.1 §7 | None known | Share with PRD v3.1
PRD v3.0 and its diagrams PDF | Word + PDF | 14 Oct 2026 | Reference | Previous version | Superseded by v3.1 | None
Therapist user flow (Word) | Word | 14 Oct 2026 | Out of date | Therapist flow as agreed on 14 Oct (D-017) | Superseded by PRD v3.1 §7.2 | Retire, or rebuild from §7.2 once the client confirms
Therapist flow draft v2 + swimlane | PDF | 18 / 22 Oct 2026 | Draft — with client | Therapist flow sent for review | Swimlane predates the 22 Oct review; PRD v3.1 §7.2 and Figures 3–4 hold the latest | Redraw the swimlane after client feedback
Clinic onboarding flow (Word) | Word | 14 Oct 2026 | Out of date | Onboarding as agreed on 14 Oct (D-018) | Superseded by PRD v3.1 §7.5 (KAM only) | Retire, or rebuild from §7.5 once the client confirms
Clinic onboarding draft v2 | PDF | 21 Oct 2026 | Draft — with client | KAM-only onboarding, temp passwords, users added by clinic | Matches PRD v3.1 §7.5 | Fold into an onboarding FSD later
FSD — User creation and login v0.4 | Word | 28 Oct 2026 | Draft — internal | Screens, rules, messages, tests; role-first; one role per user; S12 Roles list; roles built from permission ticks; 14 modules | None known. TBR positions tagged pending client confirmation | Share with client (supersedes v0.2 and v0.3)
New user flow draft v3 and roles draft | PDF | 26 / 27 Oct 2026 | Reference | Earlier swimlanes | Folded into FSD v0.4 Figures 1–3 | None
Permission catalogue | Excel | 28 Oct 2026 | Draft — internal | 86 permissions in 14 modules, role defaults, 12 open points (3 decided internally on 28 Oct) | Open points await the client; RBAC list not yet received | Share with FSD v0.4; merge RBAC list when received
Design mocks (canvas) | Canvas | 27 Oct 2026 | Draft — internal | 9 screens, role-first, agreed colours and font | No Roles list (S12); Create role still uses None/View/Edit per module, not permission ticks and scope | Update to FSD v0.4 when design resumes
MongoDB schema (user creation) | Excel + PDF | 28 Oct 2026 | Draft — internal | 13 collections for user creation and login | Follows role-first and D-019 | Keep
Open questions workbook | Excel | 9 Oct 2026 | Out of date | Questions for BEST | Several answered since; new ones missing. PRD v3.1 Appendix A.2 now lists the pending items | Refresh from Appendix A.2
PRD high-level overview (online doc) | Online doc | 9 Oct 2026 | Out of date | Summary for readers | Reflects PRD v2.0 | Update from PRD v3.1 or retire
PRD changes v1 to v3.0 | Word | 12 Oct 2026 | Reference | Change history | Historical record; v3.1 changes are in its Appendix A | None
Project repo: flows, decisions, state | Markdown | 28 Oct 2026 | Agreed | Decision log D-001 to D-020; flow notes; state | Up to date | Keep current

## Conflicts
Where the documents disagree
PRD v3.0 compared with later decisions. After the 28 October consolidation every row is reflected in PRD v3.1, FSD v0.4 and the permission catalogue; rows awaiting the client are tagged PENDING CLIENT CONFIRMATION there.
# | Topic | PRD v3.0 / agreed flows say | Latest position | Source of latest | Status | Now reflected in
1 | Consent | Recorded once per patient; does not expire (D-017) | Each consent item has a validity set by BEST per clinic; one ‘valid consent on file’ check; expired item → warning, session continues | Therapist draft 18 Oct; review 22 Oct | Awaiting client | PRD v3.1 §7.2, §8.12 (tagged)
2 | Who records consent | Org Admin (D-014) or therapist (D-017) | Therapist or Org Admin (D-020) | D-020, 28 Oct | Agreed internally | PRD v3.1 §7.2, §7.4, §8.12; flow notes; catalogue CON-02
3 | Pause | Pauses device data, alerts, video; ends at pause limit (D-017) | Timeline mark only; data, alerts and video continue; alert after 10 min; no auto-end | Therapist draft 15/18 Oct | Awaiting client | PRD v3.1 §7.2 (tagged)
4 | After-session recording | Therapist uploads a transcript (D-017) | Audio device sends audio by API; configurable wait; manual trigger when audio is missing | Therapist draft 18 Oct; review 22 Oct | Awaiting client | PRD v3.1 §7.2, §8.8 (tagged)
5 | AI summary | Therapist reviews, edits and confirms; supervisor sees confirmed only | Not editable; visible to supervisor straight away; therapist can add a note | Therapist draft 15 Oct | Awaiting client | PRD v3.1 §7.2, §7.3, §8.8 (tagged)
6 | Assessment | Not in PRD | Current assessment (6 months) required; type set at client setup | Therapist draft 15 Oct; review 22 Oct | Awaiting client | PRD v3.1 §7.2, §7.4, §8.2 (tagged)
7 | Session creation | Org Admin schedules sessions, incl. CSV import (D-014) | Scheduler or BCBA creates sessions | Review 22 Oct | Pending client | PRD v3.1 §4, §7.4, §8.2 (tagged); catalogue SES-02
8 | Attachments | PDF, TXT after the session | PDF, text, JPG, video; notes typed on screen | Review 22 Oct | Agreed in review | PRD v3.1 §7.2, §8.3
9 | Clinic onboarding | Sales-assisted or self-onboarding; sign-up link with OTP (D-018) | KAM only in Phase 1; ID + temporary password; clinic adds users; active once a therapist and a supervisor exist | Onboarding draft 21 Oct | Awaiting client | PRD v3.1 §7.5, §11 (tagged)
10 | User licence count | Seats; seat used on acceptance | Active users; counts from creation (Invited, Active, Locked) | FSD v0.2; review 22 Oct | Agreed in review | PRD v3.1 §7.4, §8.11; FSD v0.4
11 | MFA | Mandatory for Org Admin and BEST roles | Mandatory for anyone with admin access; optional per user for others | FSD v0.2; review 22 Oct | Agreed in review | PRD v3.1 §7.1, §8.1; FSD v0.4
12 | Roles | Fixed roles; Supervisor may also hold Org Admin with a view switch (D-016) | Predefined and custom roles; one role per user; no view switch (D-019) | D-019 | Agreed internally | PRD v3.1 §4, §7.1, §7.4, §8.9, §16; FSD v0.4; catalogue (ACC-05 removed)
13 | Per-user permissions | — | None outside the role; edit the role or create a new one (confirmed internally 28 Oct, D-021) | Role-first proposal 27 Oct; D-021 | Awaiting client | FSD v0.4 BR-07; PRD v3.1 §7.4, §11 (tagged)
14 | Password re-entry | Not in PRD | Before deactivating a user, creating an admin user, saving an admin role | FSD v0.2 | Agreed in review | PRD v3.1 §8.1; FSD v0.4 BR-18
15 | Inactive licence | No new sessions; view records only | View-only incl. client personal details; grey screen + label | FSD v0.2; review 22 Oct | Agreed in review | PRD v3.1 §7.1, §7.5, §8.11
16 | Login | Email + password; MFA for admins | Plus temporary password at first login, forgot password, lockout after 5 | FSD v0.2 | Agreed | PRD v3.1 §7.1, §8.1
17 | Regional formats | Not in PRD | US formats now; phone and certification lists configurable | Review 22 Oct | Agreed in review | PRD v3.1 §6
18 | Design system | Not in PRD | Blue, white, green; Poppins; trends with detail on hover | Review 22 Oct | Agreed in review | PRD v3.1 §6
19 | Database | Not in PRD | MongoDB, shared collections with an organization ID | 28 Oct | Agreed internally | PRD v3.1 §6, §14
20 | Audio and video recording | PRD v3.0 §12.1, §17.3, §17.8, §17.9: no audio or video recorded or stored | Session audio and call recordings used for the summary, subject to consent; retention to be set | Therapist drafts 15/18 Oct | Awaiting client | PRD v3.1 §12.1, §12.3, §17 (tagged)
21 | Summary confirmation elsewhere in PRD | PRD v3.0 §10, §15.1, §15.2, §16.2, §16.3: mandatory therapist confirmation | Follows the AI summary row above | Therapist draft 15 Oct | Awaiting client | PRD v3.1 §10, §15, §16 (tagged)
22 | Admin elevation | PRD v3.0 §8.1, §8.9, §13.3, §16.1: Supervisor gets admin rights by explicit elevation | Admin access only through a role with Users & roles or Clinic settings | D-019 | Agreed internally | PRD v3.1 §8.1, §8.9, §13.3, §16.1
23 | Licence renewal | License extended | Renewal creates a new licence record; history kept; one active at a time | D-019 | Agreed internally | PRD v3.1 §7.5, §8.11
24 | Module list | FSD v0.2: 10 modules | 14 modules (adds My account, Supervision, Devices, Support access) | D-021, 28 Oct | Agreed internally | FSD v0.4 §2.2 (tagged); catalogue open point 4
25 | Permission granularity | FSD: access set per module (None, View, Edit) | Ticks per permission, grouped by module, with a scope per permission | D-021, 28 Oct | Agreed internally | FSD v0.4 §2.2, S4, BR-26 (tagged); catalogue open point 11
26 | Org Admin and sessions | FSD v0.4: Org Admin has no Sessions access; D-014: Org Admin schedules sessions | Scheduling only (SES-01 to SES-05); no session content | D-021, 28 Oct | Agreed internally | FSD v0.4 §2.2 (tagged); catalogue open point 12